WORKPLAN FOR THE COMPLETION OF THESIS

# AUTHENTICATION OF WIRELESS DEVICES USING RADIO FREQUENCY FINGERPRINTING

The remaining phases of the RFF project will be carried out according to the tentative schedule.  While a significant effort will be made to adhere to the following deadlines, deviations are possible and to be expected.  The quality of research is our key motivator.

Establishment of the Infrastructure

Before we can proceed with the remaining phases, the infrastructure has to be in place.  More specifically, the acquisition of additional units of Bluetooth and 802.11b devices must be completed as soon as possible.  We anticipate the completion of the infrastructure by October 31, 2003 although an earlier date would prove beneficial in carrying out activity 1.

PHASE 2	Characterization and Classification of Transceiverprint

| Activity / Deliverable | Time Frame |
| --- | --- |
| Create different profiles using amplitude, phase and frequency, as deemed appropriate for each transceiver Establish the degree of consistency and variance for a given make and model Deliverable: Profiles Document | Oct. – Dec. 2003 |
| Analyze current approaches and implement those which are appropriate Deliverable: Analysis Document | Jan. – March 2004 |
| Endeavor to establish the DNA strand for a transceiver and test its accuracy using an appropriate classification tool Deliverable: Description of the DNA strand | Jan. – March 2004 |

PHASE 3	Development and Simulation of New Authentication Protocol

| Activity / Deliverable | Time Frame |
| --- | --- |
| Develop a generic authentication protocol using RFF and analyze it for security vulnerabilities Deliverable: Description of the Protocol | April – Sept. 2004 |
| Implement protocol Deliverable: Results of test cases | April – Sept. 2004 |
| Simulate protocol in software for the time being Deliverable: Confirmation of results of test cases in activity 6 | April – Sept. 2004 |

Submission of Thesis

It is our goal to submit the thesis for approval by December 31, 2004.